## Sheet1
ID | Modules | Story | Sprint | Product Owner
1 | Basic UI implementation | Implement the UI design of wireframe by HTML + CSS. Construct the framework of the whole webapp. Leave the to-do sections static. Using Django Template, Form, and ModelForm. | 1 | Yi Yang Andrewid: yiy3
2 | Login and Registration Page | User should be able to register via email address and login using their email account. | 1
3 | Global Stream Page | User should be able to see the lists of differents tables where other users playing games on global stream. User can choose to Create a New Room or Join the Existing Room in global stream | 1
4 | Poker System (deck, hand evaluation and compare hands) | Use proper way to express poker deck. Implement all the functions to evaluate the rank of hands, keep the name of different, return the name of poker hands. | 1
5 | Subset I of Texas Hold'em (1 vs 1, deal and act) | User is able to play game with one autoplayer (server side). User can choose check, or bet based on community card and hands. The game will end after user click bet. http://www.table-games-online.com/ultimate-texas-holdem/ | 1
6 | Autoplayer I (1 vs 1, never fold) | Server side will act as autoplayer and never fold its hand. | 1
7 | Rejoin Game | draft implement the data model to ensure the data integrity in case user is disconnected from the server. | 1 | Shiqi Jia Andrewid: shiqij
8 | Subset II of Texas Hold'em (Action: Fold, Call) | Users are able to play games with other users. But they can only choose to fold or call for each round. The game will end as general Texas Hold'em Game: showndown or everyone else fold. | 2
9 | Online chatting by text | Chatting system implemented in each game. Only support text communication | 2
10 | Autoplayer II (act based on probability) | Server slide will calculate the probability of winning if keep calling. | 2
11 | Full Version of Texas Hold'em (Added Action: Check, Bet) | Implement the full version of Texas Hold'em Game | 3 | Maoan Wang Andrewid: maoanw
12 | UI Improvement | UI improvement | 3
13 | Home Page and Ranking Page | User can check his playing history in home page. Ranking page will show the point ranking. Implement more social connection between users | 3
14 | Data Model Improvement | Data Model Improvement | 3
15 | Online chatting support emoticon | Support chatting using images | 3