## product backlog
Product Owner | ID | Story | TaskID | Task | Task Owner | Estimate Effort | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19
Shiqi Jia AndrewID:shiqij | 1 | Draft implement the data model to ensure the data integrity in case user is disconnected from the server. | 1.1 | Server Side | Shiqi Jia | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 3 | 0 |  |  |  | 10
|  |  | 1.2 | Cleint Side | Maoan Wang | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 3
| 2 | Users can choose to fold or call or check for each round. The game will end as general Texas Hold'em Game: showndown or everyone else fold. | 2.1 | Server Side | Yi Yang | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 4 | 4 | 3 | 1 | 0 | 5
|  |  | 2.2 | Clock function | Shiqi Jia | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 0 |  | 10
|  |  | 2.3 | Client Side | Shiqi Jia | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 |  | 8
|  |  | 2.4 | Data Model | Yi Yang | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | 2.5 | Side Pot Function | Maoan Wang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 0 | 0 | 0 | 5
|  |  | 2.6 | UI update | Maoan Wang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 5
|  |  | 2.7 | Room creation | Shiqi Jia | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| 3 | Additional User functions: | 3.1 | Room Display and Selection | Maoan Wang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0 | 0 | 0 | 5
|  |  | 3.3 | Game Helper Page | Yi Yang | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | 3.4 | Profile update | Yi Yang | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 5
|  |  | 3.3 | UI design |  | 5 | [12 empty] | 5
| 4 | Users are able to play games with other users. | 4.1 | Server Side | Maoan Wang | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 20
|  |  | 4.2 | Client Side | Shiqi Jia | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 3 | 0 | 0 | 10
|  |  | 4.3 | Web Socket | Yi Yang | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | 4.4 | Data Model | Maoan Wang | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4.3
[5 empty] | Total Hours Remains | 124 | 118 | 117 | 109 | 105 | 91 | 66 | 51 | 37 | 28 | 17 | 2 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## sprint2
ID | Modules | Story | Sprint | Product Owner
1 | Rejoin Game | draft implement the data model to ensure the data integrity in case user is disconnected from the server. | 2 | Shiqi Jia
2 | Subset II of Texas Hold'em (Action: Fold, Call) | Users can choose to fold or call or check for each round. The game will end as general Texas Hold'em Game: showndown or everyone else fold. | 2
3 | Online chatting by text | Chatting system implemented in each game. Only support text communication | 2
4 | Multiplayer | Users are able to play games with other users. | 2