## product backlog
ID | Modules | Story | Sprint | Task Ownner | Estimate Effort | Product Owner
1 | Call Check Function | User can choose to call or check in game | 3 | Maoan Wang | 10 - 20 h | Maoan Wang
2 | Chat Room | Users can chat during the game | 3 | Shiqi Jia | 10 h
3 | Ranking Page | Ranking page will show the users with top accumulated chips | 3 | Maoan Wang | 3 h
4 | Deploy game on AWS | Deploy game on cloud | 3 | Yi Yang | 10 h
5 | UI Improvement | Improve UI | 3 | Shiqi Jia | 10 h
6 | Function Improvement | Improve and modify current Functions | 3 | Maoan Wang | 10 h
7 | Clock Function | Complete the clock function | 3 | Yi Yang | 10 h